NYN GOLF

Year 1 Operational Plan & Timeline

1. Year 1 Overview

This operational plan outlines the month-by-month execution strategy for NYN Golf's first year of operations, beginning March 2025 with the founder's relocation to Vietnam.

| Phase | Timeline |
| --- | --- |
| Foundation | Months 1-3 (Mar-May 2025): Setup, systems, pre-launch marketing |
| Launch | Months 4-6 (Jun-Aug 2025): First trips, refine operations, gather testimonials |
| Growth | Months 7-9 (Sep-Nov 2025): Scale marketing, peak season preparation |
| Scale | Months 10-12 (Dec-Feb 2026): Peak season execution, Year 2 planning |

2. Phase 1: Foundation (Months 1-3)

Month 1: March 2025 — Vietnam Establishment

| Week | Activities | Deliverables |
| --- | --- | --- |
| Week 1 | Arrive Vietnam; secure housing; open local bank account | Housing secured |
| Week 2 | Begin business registration process; meet with attorney | Legal engagement |
| Week 3 | Visit Da Nang golf courses; begin vendor negotiations | Course tour complete |
| Week 4 | Visit hotels and restaurants; establish vendor relationships | 5+ vendor meetings |

Key Milestone: On-ground presence established

Month 2: April 2025 — Systems & Content

| Week | Activities | Deliverables |
| --- | --- | --- |
| Week 1 | Website development kickoff; domain/hosting setup | Domain live |
| Week 2 | Photography/video shoots at golf courses | Content library |
| Week 3 | Email platform setup; welcome sequence drafted | Email system ready |
| Week 4 | CRM/booking system configuration | Booking flow tested |

Key Milestone: Technology infrastructure complete

Month 3: May 2025 — Pre-Launch Marketing

| Week | Activities | Deliverables |
| --- | --- | --- |
| Week 1 | Website launch; VR tour integration | Website live |
| Week 2 | Social media launch; content calendar execution begins | Channels active |
| Week 3 | Paid advertising campaign launch ($50-100/day) | Ads running |
| Week 4 | Waitlist building; founding member outreach | 100+ waitlist signups |

Key Milestone: Marketing engine operational; waitlist building

3. Phase 2: Launch (Months 4-6)

Month 4: June 2025 — First Bookings

| Week | Activities | Deliverables |
| --- | --- | --- |
| Week 1-2 | Discovery calls with qualified leads; first bookings | First 2-3 deposits |
| Week 3-4 | Finalize Q4 trip dates; vendor confirmations | Q4 calendar set |

Key Milestone: First paying customers secured

Month 5: July 2025 — Soft Launch Trip

| Week | Activities | Deliverables |
| --- | --- | --- |
| Week 1 | Pre-trip logistics finalization | All vendors confirmed |
| Week 2 | PILOT TRIP: First group (friends/family rate) | Trip executed |
| Week 3-4 | Debrief; gather feedback; refine operations | Ops playbook updated |

Key Milestone: First trip completed; operations validated

Month 6: August 2025 — Testimonials & Refinement

| Week | Activities | Deliverables |
| --- | --- | --- |
| Week 1-2 | Collect testimonials/photos from pilot trip | 3+ testimonials |
| Week 3-4 | Update marketing with real customer stories; ramp ads | New ad creative |

Key Milestone: Social proof assets ready for peak season push

4. Phase 3: Growth (Months 7-9)

Month 7: September 2025 — Peak Season Prep

- Increase ad spend to $150-200/day for peak season bookings

- Launch corporate/President's Club outreach campaign

- Execute second paid trip; gather more testimonials

- Hire part-time local operations assistant

Target: 4-6 trips booked for Oct-Dec 2025

Month 8: October 2025 — Peak Season Begins

- Execute 2-3 trips this month (peak weather)

- Build referral pipeline from satisfied customers

- Begin YouTube content strategy (course tours)

Target: 10+ total bookings YTD

Month 9: November 2025 — Full Operations

- Execute 2-3 trips; operations running smoothly

- Launch referral program ($500 credit for referrals)

- Q1 2026 trip calendar published

Target: First repeat customer booking

5. Phase 4: Scale (Months 10-12)

Month 10: December 2025 — Holiday Peak

- Execute 3-4 trips (holiday travel surge)

- Holiday gift certificate campaign

- Year-end customer appreciation outreach

Month 11: January 2026 — Year 2 Planning

- Execute 2-3 trips

- Financial review and Year 2 projections

- Evaluate hiring full-time operations manager

- Thailand/Cambodia expansion research

Month 12: February 2026 — Year 1 Complete

- Execute 2-3 trips

- Investor update with Year 1 results

- Year 2 marketing calendar finalized

6. Year 1 Success Metrics

| Metric | Target | Stretch Goal |
| --- | --- | --- |
| Trips Completed | 15-20 | 25+ |
| Total Guests Served | 150-200 | 250+ |
| Revenue | $600K-$900K | $1M+ |
| Net Promoter Score | 70+ | 80+ |
| Repeat/Referral Rate | 20% | 30%+ |
| Email List Size | 2,000 | 5,000+ |
| Website Monthly Visitors | 5,000 | 10,000+ |

7. Go/No-Go Decision Points

Key milestones that will determine whether to continue, pivot, or pause:

| Checkpoint | Success Criteria | Action if Not Met |
| --- | --- | --- |
| Month 3 | 100+ waitlist signups; website live | Extend pre-launch; adjust messaging |
| Month 6 | 5+ deposits; pilot trip successful | Pause paid marketing; focus on referrals |
| Month 9 | 10+ trips booked; positive testimonials | Evaluate pivot to corporate-only model |
| Month 12 | 15+ trips completed; break-even achieved | Reassess Year 2 with investor |