NYN GOLF

Risk Analysis & Mitigation Strategy

This document identifies key risks facing NYN Golf and outlines specific mitigation strategies. Acknowledging and planning for risks demonstrates operational maturity and protects investor capital.

1. Risk Assessment Matrix

| Risk Category | Likelihood | Impact | Overall Rating |
| --- | --- | --- | --- |
| Market/Demand Risk | Medium | High | HIGH - Requires active monitoring |
| Operational Risk | Medium | Medium | MEDIUM - Manageable with planning |
| Financial Risk | Low | High | MEDIUM - Capital buffer in place |
| Competitive Risk | Medium | Medium | MEDIUM - Differentiation strategy |
| Regulatory/Political Risk | Low | High | LOW-MEDIUM - Vietnam stable |
| Key Person Risk | Medium | High | HIGH - Single founder dependency |

2. Detailed Risk Analysis & Mitigation

2.1 Market/Demand Risk

Risk: Insufficient demand from target market; slower-than-projected bookings

Mitigation Strategies:

- Extensive pre-launch validation: Build email waitlist of 500+ qualified prospects before first trip

- Founding member pricing: $500 discount creates urgency and early adopters

- Corporate market diversification: Pursue President's Club and incentive trip contracts as secondary revenue stream

- Flexible capacity: No fixed costs for trip delivery—scale up/down with demand

- Geographic expansion option: Thailand, Cambodia, Philippines if Vietnam demand lags

2.2 Operational Risk

Risk: Service delivery failures; vendor reliability issues; quality control problems

Mitigation Strategies:

- Founder on-ground: Steve living in Vietnam enables direct oversight and relationship management

- Vendor redundancy: 2-3 backup options for each critical service (hotels, transport, restaurants)

- Pre-trip site visits: Personal inspection of all venues before client arrival

- Event expertise: 200 corporate events experience informs contingency planning

- Real-time communication: Group WhatsApp and 24/7 founder availability during trips

2.3 Financial Risk

Risk: Cash flow challenges; cost overruns; currency fluctuation

Mitigation Strategies:

- Deposit structure: 25% deposit at booking covers customer acquisition cost immediately

- Full payment 60 days prior: All vendor costs secured before trip delivery

- Working capital reserve: $12,000 buffer included in use of funds

- Low fixed costs: No office lease, no full-time staff initially—variable cost model

- Currency hedging: Price packages in USD, negotiate VND-fixed vendor contracts where possible

2.4 Competitive Risk

Risk: Established operators copy model; price competition; new entrants

Mitigation Strategies:

- Differentiation: "Life experience" positioning—golf + culture, not just golf

- On-ground advantage: American founder living in Vietnam is hard to replicate quickly

- Brand building: Content marketing establishes thought leadership before competitors enter

- Relationship moat: Personal client relationships and referral network compound over time

- First-mover advantage: Early brand recognition in emerging market segment

2.5 Regulatory/Political Risk

Risk: Vietnam policy changes; visa restrictions; business registration challenges

Mitigation Strategies:

- Pro-tourism government: Vietnam actively promoting golf tourism with $1B target

- Greg Norman ambassadorship: Government partnership signals long-term commitment

- Legal counsel: Local attorney on retainer for business registration and compliance

- US entity structure: Primary business entity in US provides stability

- E-visa expansion: Vietnam continuing to ease tourist entry requirements

2.6 Key Person Risk

Risk: Business dependent on single founder; illness, burnout, or departure

Mitigation Strategies:

- Documentation: All processes, vendor relationships, and playbooks documented from day one

- Local team development: Hire and train Vietnamese operations manager by Month 6

- Advisory network: Golf industry contacts who could step in for client-facing roles if needed

- Insurance: Key person insurance policy once revenue supports premium

- Founder commitment: Relocation to Vietnam demonstrates long-term dedication

3. External Risk Factors

| External Risk | Likelihood | Response Plan |
| --- | --- | --- |
| Global recession | Low-Medium | Shift to corporate incentive market; offer payment plans |
| Pandemic/travel restrictions | Low | Pivot to domestic Vietnam tourism; pause & preserve capital |
| Natural disaster (typhoon) | Low | Trip rescheduling policy; travel insurance requirement |
| US-Vietnam relations deterioration | Very Low | Expand to Thailand/Cambodia; monitor State Dept advisories |
| Fuel price spike | Medium | Fuel surcharge clause in contracts; renegotiate transport |

4. Risk Management Summary

NYN Golf's risk profile is manageable for several reasons:

- Variable cost model: No fixed costs for trip delivery means break-even is achievable with 8-10 trips

- Cash-positive structure: Deposits and advance payments eliminate cash flow risk

- Favorable market timing: Government-backed tourism growth creates tailwinds

- Experienced operator: Founder's event expertise reduces operational risk

- Capital preservation: Working capital reserve and low burn rate protect investment